## Blad1
Planning | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
Plan Van Aanpak | bar: Week 1
Planning | bar: Week 1
Zevensprong | bar: Week 1
Gebruikersscenario | bar: Week 2
Procesboom | bar: Week 3
Pakket Van Eisen | bar: Week 3
Schetsen | bar: Week 4
Tussenpresentatie | bar: Week 5
Spuugmodellen | bar: Week 6
CAD ontwerp | bar: Week 7 to Week 8
Werktekening | bar: Week 7 to Week 8
Werkvoorbereiding | bar: Week 7 to Week 8
Prototype | bar: Week 7 to Week 8
Eindpresentatie | bar: Week 9
Brian Egelmeers MTD1A4